## Sheet1
Category | Apigee Functionality | Tool Feature Status | Test Status | Complexity | Efforts required for Standard Features Addition to Tool (in Days) | Remark
Enviromental Dependencies | Shared Flows | N |  | Complex | 10 | These are environmental dependencies of Proxies, which needs to be migrated first
| Flow Hooks | N |  | Complex | 3
| Target Servers | N |  | Medium | 3
| KVM Stores | N |  | Complex | 3
Proxy Skeleton | Proxy Metadata File | Y |  | Simple |  | These are the xml based proxy configuration files
| Proxy Endpoint | Y |  | Depends
| Target Endpoint | Y |  | Depends
| Flows | Y |  | Depends
| Route Rules | Y |  | Depends
Apigee Policies-Traffic Management | Spike Arrest | Y |  | Simple
| Quota | Y |  | Simple
| Reset Quota | Y |  | Simple
| Response Cache | Y |  | Simple
| Invalidate Cache | Y |  | Medium
| Populate Cache | Y |  | Medium
| Lookup Cache | Y |  | Medium
Apigee Polcies-Mediation | AssignMessage | Y |  | Depends
| ExtractVariables | N |  | Depends | 2
| AccessEntity | N |  | Medium | 2
| JSONToXML | N |  | Simple | 2
| XMLToJSON | N |  | Simple | 2
| RaiseFault | Y |  | Medium
| SOAPMessageValidation | N |  | Complex | 3
| OASValidation | N |  | Complex | 3
| KeyValueMapOperations | N |  | Complex | 2
| XSLTransform | N |  | Complex | 3
| PublishMessage | N |  | Complex | 2
| ReadPropertySet | N |  | Medium | 3
| GraphQL | N |  | Complex | 3
| CORS | Y |  | Simple
| HTTPModifier | N |  | Medium | 3
Apigee Polcies-Security | AccessControl | Y |  | Simple |  | These will mostly require third party applications ready to be integrated
| BasicAuthentication | Y |  | Simple
| HMAC | Y |  | Medium
| JWT Policies | Y |  | Medium
| DecodeJWT | Y |  | Medium
| VerifyJWT | Y |  | Medium
| GenerateJWT | Y |  | Medium
| DecodeJWS | Y |  | Medium
| VerifyJWS | Y |  | Medium
| GenerateJWS | Y |  | Medium
| OAuthV2 | N |  | Medium | 3
| GetOAuthV2Info | N |  | Medium | 1
| DeleteOAuthV2Info | N |  | Medium | 1
| SetOAuthV2Info | N |  | Medium | 1
| RevokeOAuthV2 | N |  | Medium | 1
| VerifyAPIKey | Y |  | Simple
| LDAP (OPDK only) | N |  | Medium | 2
| SAMLAssertion | N |  | Complex | 3
| JSONThreatProtection | N |  | Complex | 2
| XMLThreatProtection | N |  | Complex | 2
| RegularExpressionProtection | N |  | Complex | 3
| VerifyIAM (Apigee X/Hybrid) | N |  | Complex
Apigee Polcies-Extension | ServiceCallout | N |  | Complex | 3 | These require extensive work and third party dependencies
| JavaCallout | N |  | Complex | 3
| JavaScript | N |  | Complex | 3
| PythonScript | N |  | Complex | 3
| ExtensionCallout | N |  | Complex | 3
| FlowCallout | N |  | Complex | 3
| MessageLogging | Y |  | Simple
| StatisticsCollector | N |  | Complex | 3
| ExternalCallout | N |  | Complex | 3
| AssertCondition | N |  | Complex | 3
Apigee Polcies-AI/LLM-Specific | SemanticCacheLookup | N |  | Complex | Research | These are AI based Functionalities may or may not be adoptable
| SemanticCachePopulate | N |  | Complex | Research
| SanitizeUserPrompt | N |  | Complex | Research
| SanitizeModelResponse | N |  | Complex | Research
Declaration
All migrations are based on standard configurational mappings. For any advanced configurations there will be requirement of enhancement
Referances
Terminologies |  |  |  | Explanations
Depends |  |  |  | Depends In the complexities section it indicates its not fixed to simple/medium/complex. Base on the count, size or logic it can be evaluated to any one of the complexities.